## Dental_Pharma-ProjectData_en
Project ID | Project Type | Country | Phase | Start Date | Actual_Duration | Actual_Cost | Planned_Duration | Planned_Cost | Var_Deliverables
6 | Marketing - Launch of new product | Albania | Phase 4 - Manufacturing | 2017-09-07 09:00 | 21.5 | 553500 | 18 | 450000 | -0.13
6 | Marketing - Launch of new product | Albania | Phase 1 - Planning | 2017-12-06 09:00 | 36.5 | 61500 | 30.5 | 50000 | -0.13
6 | Marketing - Launch of new product | Albania | Phase 2 - Initiation | 7/19/17 9:00 | 27.5 | 123000 | 23 | 100000 | -0.13
6 | Marketing - Launch of new product | Albania | Phase 3 - Implementation | 2017-10-07 09:00 | 27 | 184500 | 22.5 | 150000 | -0.13
68 | IT - CRM Implementation | Albania | Initiation | 8/25/17 9:00 | 6 | 336 | 6 | 350 | -0.07
68 | IT - CRM Implementation | Albania | Preparation | 2017-12-06 09:00 | 73.5 | 7728 | 59.5 | 8050 | -0.07
68 | IT - CRM Implementation | Albania | Development | 6/18/17 9:00 | 53 | 10080 | 49 | 10500 | -0.07
68 | IT - CRM Implementation | Albania | Testing | 2017-04-08 09:00 | 20 | 2688 | 7 | 2800 | -0.07
68 | IT - CRM Implementation | Albania | Deployment | 2017-02-07 09:00 | 12 | 0 | 9 | 0 | -0.07
68 | IT - CRM Implementation | Albania | Post-deployment | 6/24/17 9:00 | 5 | 1344 | 5 | 1400 | -0.07
A | Marketing - Launch of new product | Belarus | Phase 1 - Planning | 6/26/17 9:00 | 38 | 48000 | 30.5 | 50000 | -0.03
A | Marketing - Launch of new product | Belarus | Phase 2 - Initiation | 2017-03-08 09:00 | 28.5 | 96000 | 23 | 100000 | -0.03
A | Marketing - Launch of new product | Belarus | Phase 4 - Manufacturing | 7/24/17 9:00 | 22.5 | 432000 | 18 | 450000 | -0.03
A | Marketing - Launch of new product | Belarus | Phase 3 - Implementation | 7/25/17 9:00 | 28 | 144000 | 22.5 | 150000 | -0.03
76 | IT - CRM Implementation | Belarus | Initiation | 8/26/17 9:00 | 5 | 448 | 5 | 350 | -0.12
76 | IT - CRM Implementation | Belarus | Preparation | 6/26/17 9:00 | 60.5 | 10304 | 57.5 | 8050 | -0.12
76 | IT - CRM Implementation | Belarus | Development | 2017-01-07 09:00 | 44 | 13440 | 44 | 10500 | -0.12
76 | IT - CRM Implementation | Belarus | Testing | 2017-09-08 09:00 | 16.5 | 3584 | 15.5 | 2800 | -0.12
76 | IT - CRM Implementation | Belarus | Deployment | 7/13/17 9:00 | 10 | 0 | 10 | 0 | -0.12
76 | IT - CRM Implementation | Belarus | Post-deployment | 2017-06-07 09:00 | 4 | 1792 | 4 | 1400 | -0.12
9 | Marketing - Launch of new product | Belgium | Phase 4 - Manufacturing | 2017-02-08 09:00 | 41 | 1071000 | 36 | 900000 | 0
9 | Marketing - Launch of new product | Belgium | Phase 3 - Implementation | 2017-03-08 09:00 | 51 | 357000 | 45 | 300000 | 0
9 | Marketing - Launch of new product | Belgium | Phase 1 - Planning | 2017-12-06 09:00 | 69 | 119000 | 61 | 100000 | 0
9 | Marketing - Launch of new product | Belgium | Phase 2 - Initiation | 8/20/17 9:00 | 52 | 238000 | 46 | 200000 | 0
53 | IT - CRM Implementation | Belgium | Initiation | 10/20/17 9:00 | 11 | 749 | 11 | 700 | -0.08
53 | IT - CRM Implementation | Belgium | Preparation | 2017-12-06 09:00 | 130 | 17227 | 127 | 16100 | -0.08
53 | IT - CRM Implementation | Belgium | Development | 6/23/17 9:00 | 94 | 22470 | 89 | 21000 | -0.08
53 | IT - CRM Implementation | Belgium | Testing | 9/14/17 9:00 | 35 | 5992 | 15.5 | 5600 | -0.08
53 | IT - CRM Implementation | Belgium | Deployment | 7/17/17 9:00 | 21.5 | 0 | 19.5 | 0 | -0.08
53 | IT - CRM Implementation | Belgium | Post-deployment | 2017-04-07 09:00 | 8.5 | 2996 | 8.5 | 2800 | -0.08
10 | Marketing - Launch of new product | Benin | Phase 4 - Manufacturing | 6/29/17 9:00 | 13.5 | 279000 | 12 | 300000 | -0.12
10 | Marketing - Launch of new product | Benin | Phase 3 - Implementation | 6/30/17 9:00 | 17 | 93000 | 15 | 100000 | -0.12
10 | Marketing - Launch of new product | Benin | Phase 1 - Planning | 2017-12-06 09:00 | 23 | 31000 | 20.5 | 33333.3333 | -0.12
10 | Marketing - Launch of new product | Benin | Phase 2 - Initiation | 2017-05-07 09:00 | 17.5 | 62000 | 15.5 | 66666.6667 | -0.12
88 | IT - CRM Implementation | Benin | Initiation | 7/26/17 9:00 | 4 | 296.3333 | 4 | 233.3333 | -0.01
88 | IT - CRM Implementation | Benin | Preparation | 2017-12-06 09:00 | 44 | 6815.6667 | 37 | 5366.6667 | -0.01
88 | IT - CRM Implementation | Benin | Development | 6/16/17 9:00 | 32 | 8890 | 31 | 7000 | -0.01
88 | IT - CRM Implementation | Benin | Testing | 7/14/17 9:00 | 12 | 2370.6667 | 10 | 1866.6667 | -0.01
88 | IT - CRM Implementation | Benin | Deployment | 6/24/17 9:00 | 7.5 | 0 | 6.5 | 0 | -0.01
88 | IT - CRM Implementation | Benin | Post-deployment | 6/20/17 9:00 | 3 | 1185.3333 | 3 | 933.3333 | -0.01
22 | Marketing - Launch of new product | Brazil | Phase 3 - Implementation | 7/25/17 9:00 | 28 | 163500 | 22.5 | 150000 | -0.14
22 | Marketing - Launch of new product | Brazil | Phase 4 - Manufacturing | 7/24/17 9:00 | 22.5 | 490500 | 18 | 450000 | -0.14
22 | Marketing - Launch of new product | Brazil | Phase 1 - Planning | 6/26/17 9:00 | 38 | 54500 | 30.5 | 50000 | -0.14
22 | Marketing - Launch of new product | Brazil | Phase 2 - Initiation | 2017-03-08 09:00 | 28.5 | 109000 | 23 | 100000 | -0.14
97 | IT - CRM Implementation | Brazil | Initiation | 8/20/17 9:00 | 4.5 | 444.5 | 4.5 | 350 | -0.03
97 | IT - CRM Implementation | Brazil | Preparation | 6/26/17 9:00 | 54.5 | 10223.5 | 55.5 | 8050 | -0.03
97 | IT - CRM Implementation | Brazil | Development | 2017-01-07 09:00 | 39.5 | 13335 | 41.5 | 10500 | -0.03
97 | IT - CRM Implementation | Brazil | Testing | 2017-05-08 09:00 | 15 | 3556 | 21 | 2800 | -0.03
97 | IT - CRM Implementation | Brazil | Deployment | 2017-11-07 09:00 | 9 | 0 | 9 | 0 | -0.03
97 | IT - CRM Implementation | Brazil | Post-deployment | 2017-05-07 09:00 | 4 | 1778 | 4 | 1400 | -0.03
15 | Marketing - Launch of new product | Burkina Faso | Phase 4 - Manufacturing | 2017-10-07 09:00 | 11.5 | 303000 | 12 | 300000 | -0.09
15 | Marketing - Launch of new product | Burkina Faso | Phase 3 - Implementation | 2017-11-07 09:00 | 14 | 101000 | 15 | 100000 | -0.09
15 | Marketing - Launch of new product | Burkina Faso | Phase 1 - Planning | 6/26/17 9:00 | 19 | 33666.6667 | 20.5 | 33333.3333 | -0.09
15 | Marketing - Launch of new product | Burkina Faso | Phase 2 - Initiation | 7/15/17 9:00 | 14.5 | 67333.3333 | 15.5 | 66666.6667 | -0.09
90 | IT - CRM Implementation | Burkina Faso | Initiation | 2017-10-08 09:00 | 4 | 259 | 4 | 233.3333 | -0.05
90 | IT - CRM Implementation | Burkina Faso | Preparation | 6/26/17 9:00 | 45 | 5957 | 42 | 5366.6667 | -0.05
90 | IT - CRM Implementation | Burkina Faso | Development | 6/30/17 9:00 | 32.5 | 7770 | 27.5 | 7000 | -0.05
90 | IT - CRM Implementation | Burkina Faso | Testing | 7/29/17 9:00 | 12 | 2072 | 7 | 1866.6667 | -0.05
90 | IT - CRM Implementation | Burkina Faso | Deployment | 2017-08-07 09:00 | 7.5 | 0 | 7.5 | 0 | -0.05
90 | IT - CRM Implementation | Burkina Faso | Post-deployment | 2017-04-07 09:00 | 3 | 1036 | 3 | 933.3333 | -0.05
30 | Marketing - Launch of new product | Canada | Phase 1 - Planning | 6/26/17 9:00 | 78.5 | 103000 | 61 | 100000 | -0.12
30 | Marketing - Launch of new product | Canada | Phase 2 - Initiation | 9/13/17 9:00 | 59 | 206000 | 46 | 200000 | -0.12
30 | Marketing - Launch of new product | Canada | Phase 4 - Manufacturing | 8/23/17 9:00 | 46.5 | 927000 | 36 | 900000 | -0.12
30 | Marketing - Launch of new product | Canada | Phase 3 - Implementation | 8/24/17 9:00 | 58 | 309000 | 45 | 300000 | -0.12
69 | IT - CRM Implementation | Canada | Initiation | 2017-09-11 09:00 | 11.5 | 791 | 11.5 | 700 | -0.03
69 | IT - CRM Implementation | Canada | Preparation | 6/26/17 9:00 | 136 | 18193 | 128 | 16100 | -0.03
69 | IT - CRM Implementation | Canada | Development | 2017-08-07 09:00 | 98.5 | 23730 | 92.5 | 21000 | -0.03
69 | IT - CRM Implementation | Canada | Testing | 2017-03-10 09:00 | 36.5 | 6328 | 10.5 | 5600 | -0.03
69 | IT - CRM Implementation | Canada | Deployment | 2017-02-08 09:00 | 22.5 | 0 | 19.5 | 0 | -0.03
69 | IT - CRM Implementation | Canada | Post-deployment | 7/19/17 9:00 | 9 | 3164 | 9 | 2800 | -0.03
31 | Marketing - Launch of new product | China | Phase 4 - Manufacturing | 8/15/17 9:00 | 40 | 999000 | 36 | 900000 | -0.05
31 | Marketing - Launch of new product | China | Phase 2 - Initiation | 2017-02-09 09:00 | 51 | 222000 | 46 | 200000 | -0.05
31 | Marketing - Launch of new product | China | Phase 1 - Planning | 6/26/17 9:00 | 67.5 | 111000 | 61 | 100000 | -0.05
31 | Marketing - Launch of new product | China | Phase 3 - Implementation | 8/16/17 9:00 | 49.5 | 333000 | 45 | 300000 | -0.05
101 | IT - CRM Implementation | China | Initiation | 11/22/17 9:00 | 12.5 | 707 | 12.5 | 700 | 0
101 | IT - CRM Implementation | China | Preparation | 6/26/17 9:00 | 148.5 | 16261 | 100.5 | 16100 | 0
101 | IT - CRM Implementation | China | Development | 2017-09-07 09:00 | 108 | 21210 | 97 | 21000 | 0
101 | IT - CRM Implementation | China | Testing | 2017-12-10 09:00 | 40 | 5656 | 31.5 | 5600 | 0
101 | IT - CRM Implementation | China | Deployment | 2017-05-08 09:00 | 24.5 | 0 | 19.5 | 0 | 0
101 | IT - CRM Implementation | China | Post-deployment | 7/21/17 9:00 | 10 | 2828 | 10 | 2800 | 0
20 | Marketing - Launch of new product | Colombia | Phase 1 - Planning | 7/17/17 9:00 | 35 | 61000 | 30.5 | 50000 | -0.03
20 | Marketing - Launch of new product | Colombia | Phase 3 - Implementation | 8/13/17 9:00 | 26 | 183000 | 22.5 | 150000 | -0.03
20 | Marketing - Launch of new product | Colombia | Phase 4 - Manufacturing | 2017-12-08 09:00 | 21 | 549000 | 18 | 450000 | -0.03
20 | Marketing - Launch of new product | Colombia | Phase 2 - Initiation | 8/21/17 9:00 | 26.5 | 122000 | 23 | 100000 | -0.03
96 | IT - CRM Implementation | Colombia | Initiation | 2017-11-09 09:00 | 5 | 353.5 | 5 | 350 | -0.03
96 | IT - CRM Implementation | Colombia | Preparation | 7/17/17 9:00 | 56 | 8130.5 | 60 | 8050 | -0.03
96 | IT - CRM Implementation | Colombia | Development | 7/22/17 9:00 | 40.5 | 10605 | 41.5 | 10500 | -0.03
96 | IT - CRM Implementation | Colombia | Testing | 8/27/17 9:00 | 15 | 2828 | 17 | 2800 | -0.03
96 | IT - CRM Implementation | Colombia | Deployment | 2017-01-08 09:00 | 9.5 | 0 | 9.5 | 0 | -0.03
96 | IT - CRM Implementation | Colombia | Post-deployment | 7/27/17 9:00 | 4 | 1414 | 4 | 1400 | -0.03
16 | Marketing - Launch of new product | Cote d'Ivoire | Phase 4 - Manufacturing | 2017-04-08 09:00 | 14.5 | 390000 | 12 | 300000 | -0.02
16 | Marketing - Launch of new product | Cote d'Ivoire | Phase 1 - Planning | 7/17/17 9:00 | 24 | 43333.3333 | 20.5 | 33333.3333 | -0.02
16 | Marketing - Launch of new product | Cote d'Ivoire | Phase 2 - Initiation | 2017-10-08 09:00 | 18.5 | 86666.6667 | 15.5 | 66666.6667 | -0.02
16 | Marketing - Launch of new product | Cote d'Ivoire | Phase 3 - Implementation | 2017-05-08 09:00 | 18 | 130000 | 15 | 100000 | -0.02
83 | IT - CRM Implementation | Cote d'Ivoire | Initiation | 8/29/17 9:00 | 3.5 | 240.3333 | 3.5 | 233.3333 | -0.12
83 | IT - CRM Implementation | Cote d'Ivoire | Preparation | 7/17/17 9:00 | 43 | 5527.6667 | 39 | 5366.6667 | -0.12
83 | IT - CRM Implementation | Cote d'Ivoire | Development | 7/21/17 9:00 | 31.5 | 7210 | 28.5 | 7000 | -0.12
83 | IT - CRM Implementation | Cote d'Ivoire | Testing | 8/18/17 9:00 | 11.5 | 1922.6667 | 9.5 | 1866.6667 | -0.12
83 | IT - CRM Implementation | Cote d'Ivoire | Deployment | 7/29/17 9:00 | 7 | 0 | 7 | 0 | -0.12
83 | IT - CRM Implementation | Cote d'Ivoire | Post-deployment | 7/24/17 9:00 | 3 | 961.3333 | 3 | 933.3333 | -0.12
14 | Marketing - Launch of new product | Croatia | Phase 3 - Implementation | 2017-09-08 09:00 | 22 | 184500 | 22.5 | 150000 | -0.04
14 | Marketing - Launch of new product | Croatia | Phase 4 - Manufacturing | 2017-08-08 09:00 | 17.5 | 553500 | 18 | 450000 | -0.04
14 | Marketing - Launch of new product | Croatia | Phase 1 - Planning | 7/17/17 9:00 | 29.5 | 61500 | 30.5 | 50000 | -0.04
14 | Marketing - Launch of new product | Croatia | Phase 2 - Initiation | 8/16/17 9:00 | 22.5 | 123000 | 23 | 100000 | -0.04
65 | IT - CRM Implementation | Croatia | Initiation | 2017-09-09 09:00 | 4.5 | 420 | 4.5 | 350 | -0.15
65 | IT - CRM Implementation | Croatia | Preparation | 7/17/17 9:00 | 54 | 9660 | 62 | 8050 | -0.15
65 | IT - CRM Implementation | Croatia | Development | 7/22/17 9:00 | 39 | 12600 | 42 | 10500 | -0.15
65 | IT - CRM Implementation | Croatia | Testing | 8/25/17 9:00 | 14.5 | 3360 | 14.5 | 2800 | -0.15
65 | IT - CRM Implementation | Croatia | Deployment | 2017-01-08 09:00 | 9 | 0 | 9 | 0 | -0.15
65 | IT - CRM Implementation | Croatia | Post-deployment | 7/26/17 9:00 | 4 | 1680 | 4 | 1400 | -0.15
19 | Marketing - Launch of new product | Czech Republic | Phase 3 - Implementation | 2/21/18 9:00 | 42.5 | 303000 | 45 | 300000 | -0.01
19 | Marketing - Launch of new product | Czech Republic | Phase 2 - Initiation | 2018-07-03 09:00 | 43.5 | 202000 | 46 | 200000 | -0.01
19 | Marketing - Launch of new product | Czech Republic | Phase 4 - Manufacturing | 2/20/18 9:00 | 34 | 909000 | 36 | 900000 | -0.01
19 | Marketing - Launch of new product | Czech Republic | Phase 1 - Planning | 2018-08-01 09:00 | 57.5 | 101000 | 61 | 100000 | -0.01
61 | IT - CRM Implementation | Czech Republic | Initiation | 5/22/18 9:00 | 11 | 770 | 11 | 700 | -0.09
61 | IT - CRM Implementation | Czech Republic | Preparation | 2018-08-01 09:00 | 133.5 | 17710 | 116.5 | 16100 | -0.09
61 | IT - CRM Implementation | Czech Republic | Development | 1/19/18 9:00 | 97 | 23100 | 92 | 21000 | -0.09
61 | IT - CRM Implementation | Czech Republic | Testing | 4/15/18 9:00 | 36 | 6160 | 22 | 5600 | -0.09
61 | IT - CRM Implementation | Czech Republic | Deployment | 2/13/18 9:00 | 22 | 0 | 20 | 0 | -0.09
61 | IT - CRM Implementation | Czech Republic | Post-deployment | 1/30/18 9:00 | 9 | 3080 | 9 | 2800 | -0.09
39 | Marketing - Launch of new product | Denmark | Phase 4 - Manufacturing | 2017-07-09 09:00 | 41.5 | 1062000 | 36 | 900000 | -0.07
39 | Marketing - Launch of new product | Denmark | Phase 3 - Implementation | 2017-08-09 09:00 | 51.5 | 354000 | 45 | 300000 | -0.07
39 | Marketing - Launch of new product | Denmark | Phase 2 - Initiation | 9/25/17 9:00 | 52.5 | 236000 | 46 | 200000 | -0.07
39 | Marketing - Launch of new product | Denmark | Phase 1 - Planning | 7/17/17 9:00 | 70 | 118000 | 61 | 100000 | -0.07
80 | IT - CRM Implementation | Denmark | Initiation | 11/27/17 9:00 | 11 | 812 | 11 | 700 | -0.11
80 | IT - CRM Implementation | Denmark | Preparation | 7/17/17 9:00 | 132.5 | 18676 | 130.5 | 16100 | -0.11
80 | IT - CRM Implementation | Denmark | Development | 7/28/17 9:00 | 96 | 24360 | 83 | 21000 | -0.11
80 | IT - CRM Implementation | Denmark | Testing | 10/21/17 9:00 | 35.5 | 6496 | 15.5 | 5600 | -0.11
80 | IT - CRM Implementation | Denmark | Deployment | 8/22/17 9:00 | 22 | 0 | 22 | 0 | -0.11
80 | IT - CRM Implementation | Denmark | Post-deployment | 2017-08-08 09:00 | 9 | 3248 | 9 | 2800 | -0.11
1 | Marketing - Launch of new product | Ecuador | Phase 3 - Implementation | 2017-12-09 09:00 | 21.5 | 192000 | 22.5 | 150000 | -0.05
1 | Marketing - Launch of new product | Ecuador | Phase 4 - Manufacturing | 2017-12-09 09:00 | 17 | 576000 | 18 | 450000 | -0.05
1 | Marketing - Launch of new product | Ecuador | Phase 1 - Planning | 8/21/17 9:00 | 29 | 64000 | 30.5 | 50000 | -0.05
1 | Marketing - Launch of new product | Ecuador | Phase 2 - Initiation | 9/19/17 9:00 | 22 | 128000 | 23 | 100000 | -0.05
98 | IT - CRM Implementation | Ecuador | Initiation | 10/27/17 9:00 | 5.5 | 448 | 5.5 | 350 | -0.13
98 | IT - CRM Implementation | Ecuador | Preparation | 8/21/17 9:00 | 66.5 | 10304 | 53.5 | 8050 | -0.13
98 | IT - CRM Implementation | Ecuador | Development | 8/27/17 9:00 | 48 | 13440 | 45 | 10500 | -0.13
98 | IT - CRM Implementation | Ecuador | Testing | 2017-08-10 09:00 | 18 | 3584 | 17.5 | 2800 | -0.13
98 | IT - CRM Implementation | Ecuador | Deployment | 2017-08-09 09:00 | 11 | 0 | 10 | 0 | -0.13
98 | IT - CRM Implementation | Ecuador | Post-deployment | 2017-01-09 09:00 | 4.5 | 1792 | 4.5 | 1400 | -0.13
4 | Marketing - Launch of new product | Egypt | Phase 3 - Implementation | 2017-07-08 09:00 | 20.5 | 184500 | 22.5 | 150000 | -0.01
4 | Marketing - Launch of new product | Egypt | Phase 4 - Manufacturing | 2017-07-08 09:00 | 16.5 | 553500 | 18 | 450000 | -0.01
4 | Marketing - Launch of new product | Egypt | Phase 1 - Planning | 7/17/17 9:00 | 27.5 | 61500 | 30.5 | 50000 | -0.01
4 | Marketing - Launch of new product | Egypt | Phase 2 - Initiation | 8/14/17 9:00 | 21 | 123000 | 23 | 100000 | -0.01
95 | IT - CRM Implementation | Egypt | Initiation | 9/26/17 9:00 | 6 | 374.5 | 6 | 350 | -0.09
95 | IT - CRM Implementation | Egypt | Preparation | 7/17/17 9:00 | 71 | 8613.5 | 54 | 8050 | -0.09
95 | IT - CRM Implementation | Egypt | Development | 7/23/17 9:00 | 51.5 | 11235 | 43.5 | 10500 | -0.09
95 | IT - CRM Implementation | Egypt | Testing | 2017-07-09 09:00 | 19 | 2996 | 18 | 2800 | -0.09
95 | IT - CRM Implementation | Egypt | Deployment | 2017-05-08 09:00 | 12 | 0 | 10 | 0 | -0.09
95 | IT - CRM Implementation | Egypt | Post-deployment | 7/29/17 9:00 | 5 | 1498 | 5 | 1400 | -0.09
21 | Marketing - Launch of new product | Estonia | Phase 1 - Planning | 8/21/17 9:00 | 33.5 | 51000 | 30.5 | 50000 | -0.06
21 | Marketing - Launch of new product | Estonia | Phase 2 - Initiation | 9/24/17 9:00 | 25.5 | 102000 | 23 | 100000 | -0.06
21 | Marketing - Launch of new product | Estonia | Phase 3 - Implementation | 9/16/17 9:00 | 25 | 153000 | 22.5 | 150000 | -0.06
21 | Marketing - Launch of new product | Estonia | Phase 4 - Manufacturing | 9/15/17 9:00 | 20 | 459000 | 18 | 450000 | -0.06
78 | IT - CRM Implementation | Estonia | Initiation | 10/18/17 9:00 | 5 | 409.5 | 5 | 350 | -0.09
78 | IT - CRM Implementation | Estonia | Preparation | 8/21/17 9:00 | 57.5 | 9418.5 | 59.5 | 8050 | -0.09
78 | IT - CRM Implementation | Estonia | Development | 8/26/17 9:00 | 41.5 | 12285 | 42.5 | 10500 | -0.09
78 | IT - CRM Implementation | Estonia | Testing | 2017-02-10 09:00 | 15.5 | 3276 | 15 | 2800 | -0.09
78 | IT - CRM Implementation | Estonia | Deployment | 2017-06-09 09:00 | 9.5 | 0 | 9.5 | 0 | -0.09
78 | IT - CRM Implementation | Estonia | Post-deployment | 8/31/17 9:00 | 4 | 1638 | 4 | 1400 | -0.09
2 | Marketing - Launch of new product | France | Phase 3 - Implementation | 2017-09-10 09:00 | 47.5 | 273000 | 45 | 300000 | -0.08
2 | Marketing - Launch of new product | France | Phase 4 - Manufacturing | 2017-08-10 09:00 | 38 | 819000 | 36 | 900000 | -0.08
2 | Marketing - Launch of new product | France | Phase 1 - Planning | 8/21/17 9:00 | 64.5 | 91000 | 61 | 100000 | -0.08
2 | Marketing - Launch of new product | France | Phase 2 - Initiation | 10/25/17 9:00 | 48.5 | 182000 | 46 | 200000 | -0.08
52 | IT - CRM Implementation | France | Initiation | 2018-04-01 09:00 | 11.5 | 854 | 11.5 | 700 | -0.12
52 | IT - CRM Implementation | France | Preparation | 8/21/17 9:00 | 136 | 19642 | 125 | 16100 | -0.12
52 | IT - CRM Implementation | France | Development | 2017-02-09 09:00 | 98.5 | 25620 | 97.5 | 21000 | -0.12
52 | IT - CRM Implementation | France | Testing | 11/28/17 9:00 | 36.5 | 6832 | 9.5 | 5600 | -0.12
52 | IT - CRM Implementation | France | Deployment | 9/27/17 9:00 | 22.5 | 0 | 18.5 | 0 | -0.12
52 | IT - CRM Implementation | France | Post-deployment | 9/13/17 9:00 | 9 | 3416 | 9 | 2800 | -0.12
18 | Marketing - Launch of new product | Gabon | Phase 1 - Planning | 8/21/17 9:00 | 25.5 | 31666.6667 | 20.5 | 33333.3333 | -0.11
18 | Marketing - Launch of new product | Gabon | Phase 2 - Initiation | 9/16/17 9:00 | 19.5 | 63333.3333 | 15.5 | 66666.6667 | -0.11
18 | Marketing - Launch of new product | Gabon | Phase 3 - Implementation | 2017-10-09 09:00 | 19 | 95000 | 15 | 100000 | -0.11
18 | Marketing - Launch of new product | Gabon | Phase 4 - Manufacturing | 2017-09-09 09:00 | 15 | 285000 | 12 | 300000 | -0.11
87 | IT - CRM Implementation | Gabon | Initiation | 2017-10-10 09:00 | 4.5 | 226.3333 | 4 | 233.3333 | -0.12
87 | IT - CRM Implementation | Gabon | Preparation | 8/21/17 9:00 | 49.5 | 5205.6667 | 40 | 5366.6667 | -0.12
87 | IT - CRM Implementation | Gabon | Development | 8/26/17 9:00 | 36 | 6790 | 32 | 7000 | -0.12
87 | IT - CRM Implementation | Gabon | Testing | 9/26/17 9:00 | 13.5 | 1810.6667 | 5 | 1866.6667 | -0.12
87 | IT - CRM Implementation | Gabon | Deployment | 2017-04-09 09:00 | 8.5 | 0 | 6 | 0 | -0.12
87 | IT - CRM Implementation | Gabon | Post-deployment | 8/30/17 9:00 | 3.5 | 905.3333 | 3 | 933.3333 | -0.12
45 | Marketing - Launch of new product | Gambia | Phase 3 - Implementation | 2017-02-10 09:00 | 13.5 | 127000 | 15 | 100000 | -0.07
45 | Marketing - Launch of new product | Gambia | Phase 4 - Manufacturing | 2017-02-10 09:00 | 11 | 381000 | 12 | 300000 | -0.07
45 | Marketing - Launch of new product | Gambia | Phase 2 - Initiation | 2017-07-10 09:00 | 14 | 84666.6667 | 15.5 | 66666.6667 | -0.07
45 | Marketing - Launch of new product | Gambia | Phase 1 - Planning | 9/18/17 9:00 | 18.5 | 42333.3333 | 20.5 | 33333.3333 | -0.07
86 | IT - CRM Implementation | Gambia | Initiation | 2017-08-11 09:00 | 4.5 | 273 | 4.5 | 233.3333 | -0.04
86 | IT - CRM Implementation | Gambia | Preparation | 9/18/17 9:00 | 50.5 | 6279 | 38.5 | 5366.6667 | -0.04
86 | IT - CRM Implementation | Gambia | Development | 9/23/17 9:00 | 36.5 | 8190 | 33.5 | 7000 | -0.04
86 | IT - CRM Implementation | Gambia | Testing | 10/25/17 9:00 | 13.5 | 2184 | 4.5 | 1866.6667 | -0.04
86 | IT - CRM Implementation | Gambia | Deployment | 2017-02-10 09:00 | 8.5 | 0 | 6.5 | 0 | -0.04
86 | IT - CRM Implementation | Gambia | Post-deployment | 9/27/17 9:00 | 3.5 | 1092 | 3.5 | 933.3333 | -0.04
8 | Marketing - Launch of new product | Germany | Phase 1 - Planning | 2017-12-06 09:00 | 59.5 | 101000 | 61 | 100000 | -0.06
8 | Marketing - Launch of new product | Germany | Phase 2 - Initiation | 2017-11-08 09:00 | 45 | 202000 | 46 | 200000 | -0.06
8 | Marketing - Launch of new product | Germany | Phase 4 - Manufacturing | 7/26/17 9:00 | 35 | 909000 | 36 | 900000 | -0.06
8 | Marketing - Launch of new product | Germany | Phase 3 - Implementation | 7/27/17 9:00 | 44 | 303000 | 45 | 300000 | -0.06
63 | IT - CRM Implementation | Germany | Initiation | 10/27/17 9:00 | 11.5 | 784 | 11.5 | 700 | -0.15
63 | IT - CRM Implementation | Germany | Preparation | 2017-12-06 09:00 | 137 | 18032 | 108 | 16100 | -0.15
63 | IT - CRM Implementation | Germany | Development | 6/24/17 9:00 | 99.5 | 23520 | 83.5 | 21000 | -0.15
63 | IT - CRM Implementation | Germany | Testing | 9/20/17 9:00 | 37 | 6272 | 38 | 5600 | -0.15
63 | IT - CRM Implementation | Germany | Deployment | 7/19/17 9:00 | 22.5 | 0 | 20.5 | 0 | -0.15
63 | IT - CRM Implementation | Germany | Post-deployment | 2017-05-07 09:00 | 9 | 3136 | 9 | 2800 | -0.15
38 | Marketing - Launch of new product | Greece | Phase 3 - Implementation | 11/16/17 9:00 | 57.5 | 136500 | 45 | 150000 | -0.05
38 | Marketing - Launch of new product | Greece | Phase 2 - Initiation | 2017-05-12 09:00 | 58.5 | 91000 | 46 | 100000 | -0.05
38 | Marketing - Launch of new product | Greece | Phase 4 - Manufacturing | 11/15/17 9:00 | 46 | 409500 | 36 | 450000 | -0.05
38 | Marketing - Launch of new product | Greece | Phase 1 - Planning | 9/18/17 9:00 | 77.5 | 45500 | 61 | 50000 | -0.05
72 | IT - CRM Implementation | Greece | Initiation | 1/20/18 9:00 | 10.5 | 448 | 10.5 | 350 | -0.1
72 | IT - CRM Implementation | Greece | Preparation | 9/18/17 9:00 | 124 | 10304 | 114 | 8050 | -0.1
72 | IT - CRM Implementation | Greece | Development | 9/29/17 9:00 | 90 | 13440 | 89 | 10500 | -0.1
72 | IT - CRM Implementation | Greece | Testing | 12/17/17 9:00 | 33.5 | 3584 | 28 | 2800 | -0.1
72 | IT - CRM Implementation | Greece | Deployment | 10/22/17 9:00 | 20.5 | 0 | 20.5 | 0 | -0.1
72 | IT - CRM Implementation | Greece | Post-deployment | 2017-09-10 09:00 | 8.5 | 1792 | 8.5 | 1400 | -0.1
7 | Marketing - Launch of new product | Holland | Phase 1 - Planning | 9/18/17 9:00 | 79.5 | 99000 | 61 | 100000 | -0.14
7 | Marketing - Launch of new product | Holland | Phase 2 - Initiation | 2017-07-12 09:00 | 60 | 198000 | 46 | 200000 | -0.14
7 | Marketing - Launch of new product | Holland | Phase 3 - Implementation | 11/17/17 9:00 | 58.5 | 297000 | 45 | 300000 | -0.14
7 | Marketing - Launch of new product | Holland | Phase 4 - Manufacturing | 11/16/17 9:00 | 47 | 891000 | 36 | 900000 | -0.14
54 | IT - CRM Implementation | Holland | Initiation | 1/18/18 9:00 | 10 | 798 | 10 | 700 | -0.04
54 | IT - CRM Implementation | Holland | Preparation | 9/18/17 9:00 | 122 | 18354 | 114 | 16100 | -0.04
54 | IT - CRM Implementation | Holland | Development | 9/28/17 9:00 | 88.5 | 23940 | 86.5 | 21000 | -0.04
54 | IT - CRM Implementation | Holland | Testing | 12/16/17 9:00 | 32.5 | 6384 | 32 | 5600 | -0.04
54 | IT - CRM Implementation | Holland | Deployment | 10/21/17 9:00 | 20 | 0 | 20 | 0 | -0.04
54 | IT - CRM Implementation | Holland | Post-deployment | 2017-08-10 09:00 | 8 | 3192 | 8 | 2800 | -0.04
12 | Marketing - Launch of new product | Hungary | Phase 4 - Manufacturing | 2017-06-11 09:00 | 39 | 409500 | 36 | 450000 | -0.06
12 | Marketing - Launch of new product | Hungary | Phase 1 - Planning | 9/18/17 9:00 | 66 | 45500 | 61 | 50000 | -0.06
12 | Marketing - Launch of new product | Hungary | Phase 2 - Initiation | 11/23/17 9:00 | 50 | 91000 | 46 | 100000 | -0.06
12 | Marketing - Launch of new product | Hungary | Phase 3 - Implementation | 2017-07-11 09:00 | 49 | 136500 | 45 | 150000 | -0.06
59 | IT - CRM Implementation | Hungary | Initiation | 2/17/18 9:00 | 12.5 | 339.5 | 12.5 | 350 | -0.07
59 | IT - CRM Implementation | Hungary | Preparation | 9/18/17 9:00 | 152 | 7808.5 | 93 | 8050 | -0.07
59 | IT - CRM Implementation | Hungary | Development | 2017-01-10 09:00 | 110.5 | 10185 | 92.5 | 10500 | -0.07
59 | IT - CRM Implementation | Hungary | Testing | 2018-07-01 09:00 | 41 | 2716 | 44 | 2800 | -0.07
59 | IT - CRM Implementation | Hungary | Deployment | 10/29/17 9:00 | 25 | 0 | 18 | 0 | -0.07
59 | IT - CRM Implementation | Hungary | Post-deployment | 10/13/17 9:00 | 10 | 1358 | 10 | 1400 | -0.07
29 | Marketing - Launch of new product | Indonesia | Phase 1 - Planning | 10/16/17 9:00 | 34.5 | 58500 | 30.5 | 50000 | -0.1
29 | Marketing - Launch of new product | Indonesia | Phase 2 - Initiation | 11/20/17 9:00 | 26 | 117000 | 23 | 100000 | -0.1
29 | Marketing - Launch of new product | Indonesia | Phase 4 - Manufacturing | 2017-11-11 09:00 | 20.5 | 526500 | 18 | 450000 | -0.1
29 | Marketing - Launch of new product | Indonesia | Phase 3 - Implementation | 2017-11-11 09:00 | 25.5 | 175500 | 22.5 | 150000 | -0.1
99 | IT - CRM Implementation | Indonesia | Initiation | 12/28/17 9:00 | 6 | 430.5 | 6 | 350 | -0.07
99 | IT - CRM Implementation | Indonesia | Preparation | 10/16/17 9:00 | 72.5 | 9901.5 | 48.5 | 8050 | -0.07
99 | IT - CRM Implementation | Indonesia | Development | 10/22/17 9:00 | 52.5 | 12915 | 46.5 | 10500 | -0.07
99 | IT - CRM Implementation | Indonesia | Testing | 2017-08-12 09:00 | 19.5 | 3444 | 19.5 | 2800 | -0.07
99 | IT - CRM Implementation | Indonesia | Deployment | 2017-05-11 09:00 | 12 | 0 | 10 | 0 | -0.07
99 | IT - CRM Implementation | Indonesia | Post-deployment | 10/28/17 9:00 | 5 | 1722 | 5 | 1400 | -0.07
34 | Marketing - Launch of new product | Israel | Phase 1 - Planning | 10/16/17 9:00 | 62 | 108000 | 61 | 100000 | -0.03
34 | Marketing - Launch of new product | Israel | Phase 2 - Initiation | 12/17/17 9:00 | 46.5 | 216000 | 46 | 200000 | -0.03
34 | Marketing - Launch of new product | Israel | Phase 4 - Manufacturing | 2017-01-12 09:00 | 36.5 | 972000 | 36 | 900000 | -0.03
34 | Marketing - Launch of new product | Israel | Phase 3 - Implementation | 2017-02-12 09:00 | 45.5 | 324000 | 45 | 300000 | -0.03
94 | IT - CRM Implementation | Israel | Initiation | 2/27/18 9:00 | 11 | 763 | 11 | 700 | -0.06
94 | IT - CRM Implementation | Israel | Preparation | 10/16/17 9:00 | 133.5 | 17549 | 129.5 | 16100 | -0.06
94 | IT - CRM Implementation | Israel | Development | 10/27/17 9:00 | 97 | 22890 | 84 | 21000 | -0.06
94 | IT - CRM Implementation | Israel | Testing | 1/21/18 9:00 | 36 | 6104 | 18 | 5600 | -0.06
94 | IT - CRM Implementation | Israel | Deployment | 11/21/17 9:00 | 22 | 0 | 19 | 0 | -0.06
94 | IT - CRM Implementation | Israel | Post-deployment | 2017-07-11 09:00 | 9 | 3052 | 9 | 2800 | -0.06
11 | Marketing - Launch of new product | Italy | Phase 3 - Implementation | 2017-04-12 09:00 | 48 | 336000 | 45 | 300000 | -0.13
11 | Marketing - Launch of new product | Italy | Phase 4 - Manufacturing | 2017-03-12 09:00 | 38.5 | 1008000 | 36 | 900000 | -0.13
11 | Marketing - Launch of new product | Italy | Phase 2 - Initiation | 12/20/17 9:00 | 49 | 224000 | 46 | 200000 | -0.13
11 | Marketing - Launch of new product | Italy | Phase 1 - Planning | 10/16/17 9:00 | 65 | 112000 | 61 | 100000 | -0.13
56 | IT - CRM Implementation | Italy | Initiation | 2018-10-02 09:00 | 10 | 665 | 10 | 700 | -0.06
56 | IT - CRM Implementation | Italy | Preparation | 10/16/17 9:00 | 117 | 15295 | 117 | 16100 | -0.06
56 | IT - CRM Implementation | Italy | Development | 10/26/17 9:00 | 85 | 19950 | 85 | 21000 | -0.06
56 | IT - CRM Implementation | Italy | Testing | 2018-09-01 09:00 | 31.5 | 5320 | 31.5 | 5600 | -0.06
56 | IT - CRM Implementation | Italy | Deployment | 11/17/17 9:00 | 19.5 | 0 | 19.5 | 0 | -0.06
56 | IT - CRM Implementation | Italy | Post-deployment | 2017-05-11 09:00 | 8 | 2660 | 8 | 2800 | -0.06
26 | Marketing - Launch of new product | Japan | Phase 4 - Manufacturing | 2017-08-12 09:00 | 42.5 | 981000 | 36 | 900000 | -0.06
26 | Marketing - Launch of new product | Japan | Phase 2 - Initiation | 12/27/17 9:00 | 54 | 218000 | 46 | 200000 | -0.06
26 | Marketing - Launch of new product | Japan | Phase 3 - Implementation | 2017-09-12 09:00 | 53 | 327000 | 45 | 300000 | -0.06
26 | Marketing - Launch of new product | Japan | Phase 1 - Planning | 10/16/17 9:00 | 71.5 | 109000 | 61 | 100000 | -0.06
57 | IT - CRM Implementation | Japan | Initiation | 3/14/18 9:00 | 12.5 | 679 | 12.5 | 700 | -0.04
57 | IT - CRM Implementation | Japan | Preparation | 10/16/17 9:00 | 148.5 | 15617 | 112.5 | 16100 | -0.04
57 | IT - CRM Implementation | Japan | Development | 10/29/17 9:00 | 108 | 20370 | 102 | 21000 | -0.04
57 | IT - CRM Implementation | Japan | Testing | 2018-01-02 09:00 | 40 | 5432 | 15.5 | 5600 | -0.04
57 | IT - CRM Implementation | Japan | Deployment | 11/25/17 9:00 | 24.5 | 0 | 18.5 | 0 | -0.04
57 | IT - CRM Implementation | Japan | Post-deployment | 2017-10-11 09:00 | 10 | 2716 | 10 | 2800 | -0.04
44 | Marketing - Launch of new product | Jordan | Phase 3 - Implementation | 2017-07-11 09:00 | 21.5 | 162000 | 22.5 | 150000 | -0.14
44 | Marketing - Launch of new product | Jordan | Phase 1 - Planning | 10/16/17 9:00 | 29 | 54000 | 30.5 | 50000 | -0.14
44 | Marketing - Launch of new product | Jordan | Phase 4 - Manufacturing | 2017-07-11 09:00 | 17 | 486000 | 18 | 450000 | -0.14
44 | Marketing - Launch of new product | Jordan | Phase 2 - Initiation | 11/14/17 9:00 | 22 | 108000 | 23 | 100000 | -0.14
93 | IT - CRM Implementation | Jordan | Initiation | 2017-09-12 09:00 | 4.5 | 427 | 4.5 | 350 | -0.14
93 | IT - CRM Implementation | Jordan | Preparation | 10/16/17 9:00 | 54 | 9821 | 62 | 8050 | -0.14
93 | IT - CRM Implementation | Jordan | Development | 10/21/17 9:00 | 39 | 12810 | 39 | 10500 | -0.14
93 | IT - CRM Implementation | Jordan | Testing | 11/24/17 9:00 | 14.5 | 3416 | 16.5 | 2800 | -0.14
93 | IT - CRM Implementation | Jordan | Deployment | 10/31/17 9:00 | 9 | 0 | 10 | 0 | -0.14
93 | IT - CRM Implementation | Jordan | Post-deployment | 10/25/17 9:00 | 4 | 1708 | 4 | 1400 | -0.14
27 | Marketing - Launch of new product | La Reunion | Phase 4 - Manufacturing | 2017-12-12 09:00 | 23 | 468000 | 18 | 450000 | 0
27 | Marketing - Launch of new product | La Reunion | Phase 1 - Planning | 11/13/17 9:00 | 38.5 | 52000 | 30.5 | 50000 | 0
27 | Marketing - Launch of new product | La Reunion | Phase 2 - Initiation | 12/22/17 9:00 | 29 | 104000 | 23 | 100000 | 0
27 | Marketing - Launch of new product | La Reunion | Phase 3 - Implementation | 2017-12-12 09:00 | 28.5 | 156000 | 22.5 | 150000 | 0
103 | IT - CRM Implementation | La Reunion | Initiation | 1/16/18 9:00 | 5.5 | 430.5 | 5.5 | 350 | -0.04
103 | IT - CRM Implementation | La Reunion | Preparation | 11/13/17 9:00 | 64 | 9901.5 | 60 | 8050 | -0.04
103 | IT - CRM Implementation | La Reunion | Development | 11/19/17 9:00 | 46.5 | 12915 | 43.5 | 10500 | -0.04
103 | IT - CRM Implementation | La Reunion | Testing | 12/30/17 9:00 | 17.5 | 3444 | 13 | 2800 | -0.04
103 | IT - CRM Implementation | La Reunion | Deployment | 2017-01-12 09:00 | 10.5 | 0 | 9.5 | 0 | -0.04
103 | IT - CRM Implementation | La Reunion | Post-deployment | 11/24/17 9:00 | 4.5 | 1722 | 4.5 | 1400 | -0.04
3 | Marketing - Launch of new product | Lebanon | Phase 3 - Implementation | 12/13/17 9:00 | 29.5 | 189000 | 22.5 | 150000 | -0.05
3 | Marketing - Launch of new product | Lebanon | Phase 4 - Manufacturing | 12/13/17 9:00 | 23.5 | 567000 | 18 | 450000 | -0.05
3 | Marketing - Launch of new product | Lebanon | Phase 1 - Planning | 11/13/17 9:00 | 40 | 63000 | 30.5 | 50000 | -0.05
3 | Marketing - Launch of new product | Lebanon | Phase 2 - Initiation | 12/23/17 9:00 | 30 | 126000 | 23 | 100000 | -0.05
92 | IT - CRM Implementation | Lebanon | Initiation | 1/28/18 9:00 | 6.5 | 364 | 6 | 350 | -0.05
92 | IT - CRM Implementation | Lebanon | Preparation | 11/13/17 9:00 | 76 | 8372 | 60 | 8050 | -0.05
92 | IT - CRM Implementation | Lebanon | Development | 11/20/17 9:00 | 55.5 | 10920 | 48 | 10500 | -0.05
92 | IT - CRM Implementation | Lebanon | Testing | 2018-08-01 09:00 | 20.5 | 2912 | 6 | 2800 | -0.05
92 | IT - CRM Implementation | Lebanon | Deployment | 2017-04-12 09:00 | 12.5 | 0 | 10 | 0 | -0.05
92 | IT - CRM Implementation | Lebanon | Post-deployment | 11/26/17 9:00 | 5 | 1456 | 5 | 1400 | -0.05
42 | Marketing - Launch of new product | Lithuania | Phase 4 - Manufacturing | 2017-07-12 09:00 | 19 | 576000 | 18 | 450000 | -0.08
42 | Marketing - Launch of new product | Lithuania | Phase 1 - Planning | 11/13/17 9:00 | 32 | 64000 | 30.5 | 50000 | -0.08
42 | Marketing - Launch of new product | Lithuania | Phase 2 - Initiation | 12/15/17 9:00 | 24 | 128000 | 23 | 100000 | -0.08
42 | Marketing - Launch of new product | Lithuania | Phase 3 - Implementation | 2017-07-12 09:00 | 23.5 | 192000 | 22.5 | 150000 | -0.08
77 | IT - CRM Implementation | Lithuania | Initiation | 1/23/18 9:00 | 6 | 364 | 5 | 350 | -0.09
77 | IT - CRM Implementation | Lithuania | Preparation | 11/13/17 9:00 | 71 | 8372 | 60 | 8050 | -0.09
77 | IT - CRM Implementation | Lithuania | Development | 11/19/17 9:00 | 51.5 | 10920 | 47 | 10500 | -0.09
77 | IT - CRM Implementation | Lithuania | Testing | 2018-04-01 09:00 | 19 | 2912 | 7.5 | 2800 | -0.09
77 | IT - CRM Implementation | Lithuania | Deployment | 2017-02-12 09:00 | 12 | 0 | 11 | 0 | -0.09
77 | IT - CRM Implementation | Lithuania | Post-deployment | 11/25/17 9:00 | 5 | 1456 | 4 | 1400 | -0.09
43 | Marketing - Launch of new product | Luxembourg | Phase 3 - Implementation | 2018-08-01 09:00 | 54 | 378000 | 45 | 300000 | 0
43 | Marketing - Launch of new product | Luxembourg | Phase 4 - Manufacturing | 2018-06-01 09:00 | 43.5 | 1134000 | 36 | 900000 | 0
43 | Marketing - Launch of new product | Luxembourg | Phase 2 - Initiation | 1/26/18 9:00 | 55.5 | 252000 | 46 | 200000 | 0
43 | Marketing - Launch of new product | Luxembourg | Phase 1 - Planning | 11/13/17 9:00 | 73.5 | 126000 | 61 | 100000 | 0
55 | IT - CRM Implementation | Luxembourg | Initiation | 2018-03-04 09:00 | 11.5 | 847 | 11.5 | 700 | 0
55 | IT - CRM Implementation | Luxembourg | Preparation | 11/13/17 9:00 | 140.5 | 19481 | 106.5 | 16100 | 0
55 | IT - CRM Implementation | Luxembourg | Development | 11/25/17 9:00 | 102 | 25410 | 99 | 21000 | 0
55 | IT - CRM Implementation | Luxembourg | Testing | 2/23/18 9:00 | 37.5 | 6776 | 21 | 5600 | 0
55 | IT - CRM Implementation | Luxembourg | Deployment | 12/21/17 9:00 | 23 | 0 | 23 | 0 | 0
55 | IT - CRM Implementation | Luxembourg | Post-deployment | 2017-06-12 09:00 | 9.5 | 3388 | 9.5 | 2800 | 0
46 | Marketing - Launch of new product | Macedonia | Phase 4 - Manufacturing | 2017-07-12 09:00 | 19 | 585000 | 18 | 450000 | -0.14
46 | Marketing - Launch of new product | Macedonia | Phase 2 - Initiation | 12/15/17 9:00 | 24 | 130000 | 23 | 100000 | -0.14
46 | Marketing - Launch of new product | Macedonia | Phase 3 - Implementation | 2017-07-12 09:00 | 23.5 | 195000 | 22.5 | 150000 | -0.14
46 | Marketing - Launch of new product | Macedonia | Phase 1 - Planning | 11/13/17 9:00 | 32 | 65000 | 30.5 | 50000 | -0.14
67 | IT - CRM Implementation | Macedonia | Initiation | 2018-07-01 09:00 | 4.5 | 385 | 4.5 | 350 | 0
67 | IT - CRM Implementation | Macedonia | Preparation | 11/13/17 9:00 | 55 | 8855 | 55 | 8050 | 0
67 | IT - CRM Implementation | Macedonia | Development | 11/18/17 9:00 | 40 | 11550 | 43 | 10500 | 0
67 | IT - CRM Implementation | Macedonia | Testing | 12/23/17 9:00 | 15 | 3080 | 20 | 2800 | 0
67 | IT - CRM Implementation | Macedonia | Deployment | 11/28/17 9:00 | 9 | 0 | 9 | 0 | 0
67 | IT - CRM Implementation | Macedonia | Post-deployment | 11/22/17 9:00 | 4 | 1540 | 4 | 1400 | 0
13 | Marketing - Launch of new product | Malaysia | Phase 4 - Manufacturing | 2018-03-01 09:00 | 23.5 | 409500 | 18 | 450000 | 0
13 | Marketing - Launch of new product | Malaysia | Phase 1 - Planning | 2017-04-12 09:00 | 40 | 45500 | 30.5 | 50000 | 0
13 | Marketing - Launch of new product | Malaysia | Phase 2 - Initiation | 1/13/18 9:00 | 30 | 91000 | 23 | 100000 | 0
13 | Marketing - Launch of new product | Malaysia | Phase 3 - Implementation | 2018-03-01 09:00 | 29.5 | 136500 | 22.5 | 150000 | 0
100 | IT - CRM Implementation | Malaysia | Initiation | 2/13/18 9:00 | 6 | 325.5 | 6 | 350 | 0
100 | IT - CRM Implementation | Malaysia | Preparation | 2017-04-12 09:00 | 71 | 7486.5 | 56 | 8050 | 0
100 | IT - CRM Implementation | Malaysia | Development | 2017-10-12 09:00 | 51.5 | 9765 | 42.5 | 10500 | 0
100 | IT - CRM Implementation | Malaysia | Testing | 1/25/18 9:00 | 19 | 2604 | 17 | 2800 | 0
100 | IT - CRM Implementation | Malaysia | Deployment | 12/23/17 9:00 | 12 | 0 | 10 | 0 | 0
100 | IT - CRM Implementation | Malaysia | Post-deployment | 12/16/17 9:00 | 5 | 1302 | 5 | 1400 | 0
33 | Marketing - Launch of new product | Malta | Phase 2 - Initiation | 2018-03-01 09:00 | 23 | 90000 | 23 | 100000 | -0.14
33 | Marketing - Launch of new product | Malta | Phase 4 - Manufacturing | 12/27/17 9:00 | 18 | 405000 | 18 | 450000 | -0.14
33 | Marketing - Launch of new product | Malta | Phase 1 - Planning | 2017-04-12 09:00 | 30 | 45000 | 30.5 | 50000 | -0.14
33 | Marketing - Launch of new product | Malta | Phase 3 - Implementation | 12/27/17 9:00 | 22.5 | 135000 | 22.5 | 150000 | -0.14
70 | IT - CRM Implementation | Malta | Initiation | 2018-11-02 09:00 | 6 | 420 | 6 | 350 | -0.13
70 | IT - CRM Implementation | Malta | Preparation | 2017-04-12 09:00 | 69 | 9660 | 51 | 8050 | -0.13
70 | IT - CRM Implementation | Malta | Development | 2017-10-12 09:00 | 50 | 12600 | 43 | 10500 | -0.13
70 | IT - CRM Implementation | Malta | Testing | 1/23/18 9:00 | 18.5 | 3360 | 19.5 | 2800 | -0.13
70 | IT - CRM Implementation | Malta | Deployment | 12/23/17 9:00 | 11.5 | 0 | 11.5 | 0 | -0.13
70 | IT - CRM Implementation | Malta | Post-deployment | 12/16/17 9:00 | 5 | 1680 | 5 | 1400 | -0.13
49 | Marketing - Launch of new product | Mauritius | Phase 1 - Planning | 9/18/17 9:00 | 29 | 57500 | 30.5 | 50000 | -0.14
49 | Marketing - Launch of new product | Mauritius | Phase 3 - Implementation | 2017-10-10 09:00 | 21.5 | 172500 | 22.5 | 150000 | -0.14
49 | Marketing - Launch of new product | Mauritius | Phase 2 - Initiation | 10/17/17 9:00 | 22 | 115000 | 23 | 100000 | -0.14
49 | Marketing - Launch of new product | Mauritius | Phase 4 - Manufacturing | 2017-10-10 09:00 | 17 | 517500 | 18 | 450000 | -0.14
102 | IT - CRM Implementation | Mauritius | Initiation | 11/19/17 9:00 | 5.5 | 451.5 | 5.5 | 350 | -0.02
102 | IT - CRM Implementation | Mauritius | Preparation | 9/18/17 9:00 | 62 | 10384.5 | 56 | 8050 | -0.02
102 | IT - CRM Implementation | Mauritius | Development | 9/24/17 9:00 | 45 | 13545 | 44 | 10500 | -0.02
102 | IT - CRM Implementation | Mauritius | Testing | 2017-02-11 09:00 | 17 | 3612 | 15.5 | 2800 | -0.02
102 | IT - CRM Implementation | Mauritius | Deployment | 2017-05-10 09:00 | 10.5 | 0 | 10.5 | 0 | -0.02
102 | IT - CRM Implementation | Mauritius | Post-deployment | 9/29/17 9:00 | 4.5 | 1806 | 4.5 | 1400 | -0.02
47 | Marketing - Launch of new product | Niger | Phase 4 - Manufacturing | 12/20/17 9:00 | 12.5 | 270000 | 12 | 300000 | -0.11
47 | Marketing - Launch of new product | Niger | Phase 1 - Planning | 2017-04-12 09:00 | 21.5 | 30000 | 20.5 | 33333.3333 | -0.11
47 | Marketing - Launch of new product | Niger | Phase 2 - Initiation | 12/26/17 9:00 | 16 | 60000 | 15.5 | 66666.6667 | -0.11
47 | Marketing - Launch of new product | Niger | Phase 3 - Implementation | 12/20/17 9:00 | 16 | 90000 | 15 | 100000 | -0.11
91 | IT - CRM Implementation | Niger | Initiation | 2018-10-01 09:00 | 3 | 221.6667 | 3 | 233.3333 | -0.04
91 | IT - CRM Implementation | Niger | Preparation | 2017-04-12 09:00 | 36.5 | 5098.3333 | 38.5 | 5366.6667 | -0.04
91 | IT - CRM Implementation | Niger | Development | 2017-07-12 09:00 | 26.5 | 6650 | 28.5 | 7000 | -0.04
91 | IT - CRM Implementation | Niger | Testing | 12/31/17 9:00 | 10 | 1773.3333 | 12 | 1866.6667 | -0.04
91 | IT - CRM Implementation | Niger | Deployment | 12/14/17 9:00 | 6 | 0 | 6 | 0 | -0.04
91 | IT - CRM Implementation | Niger | Post-deployment | 2017-10-12 09:00 | 2.5 | 886.6667 | 2.5 | 933.3333 | -0.04
35 | Marketing - Launch of new product | Norway | Phase 2 - Initiation | 1/31/18 9:00 | 44 | 206000 | 46 | 200000 | -0.11
35 | Marketing - Launch of new product | Norway | Phase 3 - Implementation | 1/17/18 9:00 | 43 | 309000 | 45 | 300000 | -0.11
35 | Marketing - Launch of new product | Norway | Phase 1 - Planning | 2017-04-12 09:00 | 58 | 103000 | 61 | 100000 | -0.11
35 | Marketing - Launch of new product | Norway | Phase 4 - Manufacturing | 1/16/18 9:00 | 34.5 | 927000 | 36 | 900000 | -0.11
81 | IT - CRM Implementation | Norway | Initiation | 2018-02-04 09:00 | 10 | 840 | 10 | 700 | -0.11
81 | IT - CRM Implementation | Norway | Preparation | 2017-04-12 09:00 | 118.5 | 19320 | 118.5 | 16100 | -0.11
81 | IT - CRM Implementation | Norway | Development | 12/14/17 9:00 | 86 | 25200 | 85 | 21000 | -0.11
81 | IT - CRM Implementation | Norway | Testing | 2/28/18 9:00 | 32 | 6720 | 30 | 5600 | -0.11
81 | IT - CRM Implementation | Norway | Deployment | 2018-05-01 09:00 | 19.5 | 0 | 19.5 | 0 | -0.11
81 | IT - CRM Implementation | Norway | Post-deployment | 12/24/17 9:00 | 8 | 3360 | 8 | 2800 | -0.11
37 | Marketing - Launch of new product | Poland | Phase 1 - Planning | 2017-04-12 09:00 | 58 | 63000 | 61 | 50000 | -0.04
37 | Marketing - Launch of new product | Poland | Phase 3 - Implementation | 1/17/18 9:00 | 43 | 189000 | 45 | 150000 | -0.04
37 | Marketing - Launch of new product | Poland | Phase 2 - Initiation | 1/31/18 9:00 | 44 | 126000 | 46 | 100000 | -0.04
37 | Marketing - Launch of new product | Poland | Phase 4 - Manufacturing | 1/16/18 9:00 | 34.5 | 567000 | 36 | 450000 | -0.04
60 | IT - CRM Implementation | Poland | Initiation | 2018-02-05 09:00 | 12.5 | 416.5 | 12.5 | 350 | -0.12
60 | IT - CRM Implementation | Poland | Preparation | 2017-04-12 09:00 | 148.5 | 9579.5 | 104.5 | 8050 | -0.12
60 | IT - CRM Implementation | Poland | Development | 12/17/17 9:00 | 108 | 12495 | 79 | 10500 | -0.12
60 | IT - CRM Implementation | Poland | Testing | 3/22/18 9:00 | 40 | 3332 | 43.5 | 2800 | -0.12
60 | IT - CRM Implementation | Poland | Deployment | 1/13/18 9:00 | 24.5 | 0 | 21.5 | 0 | -0.12
60 | IT - CRM Implementation | Poland | Post-deployment | 12/29/17 9:00 | 10 | 1666 | 10 | 1400 | -0.12
36 | Marketing - Launch of new product | Portugal | Phase 1 - Planning | 2018-08-01 09:00 | 68 | 52500 | 61 | 50000 | -0.01
36 | Marketing - Launch of new product | Portugal | Phase 2 - Initiation | 3/17/18 9:00 | 51.5 | 105000 | 46 | 100000 | -0.01
36 | Marketing - Launch of new product | Portugal | Phase 3 - Implementation | 2018-01-03 09:00 | 50 | 157500 | 45 | 150000 | -0.01
36 | Marketing - Launch of new product | Portugal | Phase 4 - Manufacturing | 2/27/18 9:00 | 40 | 472500 | 36 | 450000 | -0.01
73 | IT - CRM Implementation | Portugal | Initiation | 4/25/18 9:00 | 9 | 420 | 9 | 350 | -0.03
73 | IT - CRM Implementation | Portugal | Preparation | 2018-08-01 09:00 | 106.5 | 9660 | 110.5 | 8050 | -0.03
73 | IT - CRM Implementation | Portugal | Development | 1/17/18 9:00 | 77.5 | 12600 | 85.5 | 10500 | -0.03
73 | IT - CRM Implementation | Portugal | Testing | 3/27/18 9:00 | 28.5 | 3360 | 41 | 2800 | -0.03
73 | IT - CRM Implementation | Portugal | Deployment | 2018-06-02 09:00 | 17.5 | 0 | 17.5 | 0 | -0.03
73 | IT - CRM Implementation | Portugal | Post-deployment | 1/26/18 9:00 | 7 | 1680 | 7 | 1400 | -0.03
28 | Marketing - Launch of new product | Russia | Phase 4 - Manufacturing | 2018-05-03 09:00 | 44.5 | 918000 | 36 | 900000 | -0.12
28 | Marketing - Launch of new product | Russia | Phase 3 - Implementation | 2018-06-03 09:00 | 55.5 | 306000 | 45 | 300000 | -0.12
28 | Marketing - Launch of new product | Russia | Phase 1 - Planning | 2018-08-01 09:00 | 75.5 | 102000 | 61 | 100000 | -0.12
28 | Marketing - Launch of new product | Russia | Phase 2 - Initiation | 3/25/18 9:00 | 57 | 204000 | 46 | 200000 | -0.12
75 | IT - CRM Implementation | Russia | Initiation | 4/24/18 9:00 | 9 | 665 | 9 | 700 | -0.12
75 | IT - CRM Implementation | Russia | Preparation | 2018-08-01 09:00 | 105.5 | 15295 | 120.5 | 16100 | -0.12
75 | IT - CRM Implementation | Russia | Development | 1/17/18 9:00 | 76.5 | 19950 | 85.5 | 21000 | -0.12
75 | IT - CRM Implementation | Russia | Testing | 3/26/18 9:00 | 28.5 | 5320 | 30.5 | 5600 | -0.12
75 | IT - CRM Implementation | Russia | Deployment | 2018-06-02 09:00 | 17.5 | 0 | 18.5 | 0 | -0.12
75 | IT - CRM Implementation | Russia | Post-deployment | 1/26/18 9:00 | 7 | 2660 | 7 | 2800 | -0.12
40 | Marketing - Launch of new product | Senegal | Phase 3 - Implementation | 1/26/18 9:00 | 18 | 108000 | 15 | 100000 | -0.12
40 | Marketing - Launch of new product | Senegal | Phase 1 - Planning | 2018-08-01 09:00 | 24 | 36000 | 20.5 | 33333.3333 | -0.12
40 | Marketing - Launch of new product | Senegal | Phase 2 - Initiation | 2018-01-02 09:00 | 18 | 72000 | 15.5 | 66666.6667 | -0.12
40 | Marketing - Launch of new product | Senegal | Phase 4 - Manufacturing | 1/26/18 9:00 | 14.5 | 324000 | 12 | 300000 | -0.12
84 | IT - CRM Implementation | Senegal | Initiation | 2/28/18 9:00 | 4.5 | 212.3333 | 4.5 | 233.3333 | -0.15
84 | IT - CRM Implementation | Senegal | Preparation | 2018-08-01 09:00 | 51 | 4883.6667 | 41 | 5366.6667 | -0.15
84 | IT - CRM Implementation | Senegal | Development | 1/13/18 9:00 | 37 | 6370 | 30 | 7000 | -0.15
84 | IT - CRM Implementation | Senegal | Testing | 2/14/18 9:00 | 14 | 1698.6667 | 5.5 | 1866.6667 | -0.15
84 | IT - CRM Implementation | Senegal | Deployment | 1/22/18 9:00 | 8.5 | 0 | 6.5 | 0 | -0.15
84 | IT - CRM Implementation | Senegal | Post-deployment | 1/17/18 9:00 | 3.5 | 849.3333 | 3.5 | 933.3333 | -0.15
50 | Marketing - Launch of new product | Serbia | Phase 4 - Manufacturing | 2018-03-02 09:00 | 20.5 | 576000 | 18 | 450000 | -0.05
50 | Marketing - Launch of new product | Serbia | Phase 1 - Planning | 2018-08-01 09:00 | 34.5 | 64000 | 30.5 | 50000 | -0.05
50 | Marketing - Launch of new product | Serbia | Phase 2 - Initiation | 2018-12-02 09:00 | 26 | 128000 | 23 | 100000 | -0.05
50 | Marketing - Launch of new product | Serbia | Phase 3 - Implementation | 2018-03-02 09:00 | 25.5 | 192000 | 22.5 | 150000 | -0.05
64 | IT - CRM Implementation | Serbia | Initiation | 2018-09-03 09:00 | 5 | 423.5 | 5 | 350 | -0.09
64 | IT - CRM Implementation | Serbia | Preparation | 2018-08-01 09:00 | 60 | 9740.5 | 60 | 8050 | -0.09
64 | IT - CRM Implementation | Serbia | Development | 1/13/18 9:00 | 43.5 | 12705 | 42.5 | 10500 | -0.09
64 | IT - CRM Implementation | Serbia | Testing | 2/21/18 9:00 | 16 | 3388 | 14.5 | 2800 | -0.09
64 | IT - CRM Implementation | Serbia | Deployment | 1/24/18 9:00 | 10 | 0 | 10 | 0 | -0.09
64 | IT - CRM Implementation | Serbia | Post-deployment | 1/18/18 9:00 | 4 | 1694 | 4 | 1400 | -0.09
41 | Marketing - Launch of new product | Slovakia | Phase 4 - Manufacturing | 2018-06-04 09:00 | 42.5 | 1071000 | 36 | 900000 | -0.11
41 | Marketing - Launch of new product | Slovakia | Phase 2 - Initiation | 4/25/18 9:00 | 54 | 238000 | 46 | 200000 | -0.11
41 | Marketing - Launch of new product | Slovakia | Phase 1 - Planning | 2018-12-02 09:00 | 71.5 | 119000 | 61 | 100000 | -0.11
41 | Marketing - Launch of new product | Slovakia | Phase 3 - Implementation | 2018-07-04 09:00 | 53 | 357000 | 45 | 300000 | -0.11
62 | IT - CRM Implementation | Slovakia | Initiation | 2018-11-07 09:00 | 12.5 | 889 | 12.5 | 700 | -0.11
62 | IT - CRM Implementation | Slovakia | Preparation | 2018-12-02 09:00 | 148.5 | 20447 | 128.5 | 16100 | -0.11
62 | IT - CRM Implementation | Slovakia | Development | 2/25/18 9:00 | 108 | 26670 | 90 | 21000 | -0.11
62 | IT - CRM Implementation | Slovakia | Testing | 5/31/18 9:00 | 40 | 7112 | 10.5 | 5600 | -0.11
62 | IT - CRM Implementation | Slovakia | Deployment | 3/24/18 9:00 | 24.5 | 0 | 19.5 | 0 | -0.11
62 | IT - CRM Implementation | Slovakia | Post-deployment | 2018-09-03 09:00 | 10 | 3556 | 10 | 2800 | -0.11
48 | Marketing - Launch of new product | Slovenia | Phase 2 - Initiation | 4/20/18 9:00 | 50.5 | 220000 | 46 | 200000 | -0.13
48 | Marketing - Launch of new product | Slovenia | Phase 3 - Implementation | 2018-04-04 09:00 | 49.5 | 330000 | 45 | 300000 | -0.13
48 | Marketing - Launch of new product | Slovenia | Phase 1 - Planning | 2018-12-02 09:00 | 66.5 | 110000 | 61 | 100000 | -0.13
48 | Marketing - Launch of new product | Slovenia | Phase 4 - Manufacturing | 2018-03-04 09:00 | 39.5 | 990000 | 36 | 900000 | -0.13
66 | IT - CRM Implementation | Slovenia | Initiation | 2018-07-07 09:00 | 12 | 896 | 12 | 700 | -0.07
66 | IT - CRM Implementation | Slovenia | Preparation | 2018-12-02 09:00 | 145 | 20608 | 139 | 16100 | -0.07
66 | IT - CRM Implementation | Slovenia | Development | 2/24/18 9:00 | 105 | 26880 | 81 | 21000 | -0.07
66 | IT - CRM Implementation | Slovenia | Testing | 5/28/18 9:00 | 39 | 7168 | 6.5 | 5600 | -0.07
66 | IT - CRM Implementation | Slovenia | Deployment | 3/23/18 9:00 | 24 | 0 | 22 | 0 | -0.07
66 | IT - CRM Implementation | Slovenia | Post-deployment | 2018-08-03 09:00 | 9.5 | 3584 | 9.5 | 2800 | -0.07
5 | Marketing - Launch of new product | South Africa | Phase 4 - Manufacturing | 2017-05-07 09:00 | 18.5 | 445500 | 18 | 450000 | -0.02
5 | Marketing - Launch of new product | South Africa | Phase 3 - Implementation | 2017-06-07 09:00 | 23 | 148500 | 22.5 | 150000 | -0.02
5 | Marketing - Launch of new product | South Africa | Phase 1 - Planning | 2017-12-06 09:00 | 31 | 49500 | 30.5 | 50000 | -0.02
5 | Marketing - Launch of new product | South Africa | Phase 2 - Initiation | 7/13/17 9:00 | 23.5 | 99000 | 23 | 100000 | -0.02
85 | IT - CRM Implementation | South Africa | Initiation | 2017-08-08 09:00 | 5 | 402.5 | 5 | 350 | -0.15
85 | IT - CRM Implementation | South Africa | Preparation | 2017-12-06 09:00 | 56.5 | 9257.5 | 58.5 | 8050 | -0.15
85 | IT - CRM Implementation | South Africa | Development | 6/17/17 9:00 | 41 | 12075 | 42 | 10500 | -0.15
85 | IT - CRM Implementation | South Africa | Testing | 7/23/17 9:00 | 15 | 3220 | 17.5 | 2800 | -0.15
85 | IT - CRM Implementation | South Africa | Deployment | 6/27/17 9:00 | 9.5 | 0 | 9.5 | 0 | -0.15
85 | IT - CRM Implementation | South Africa | Post-deployment | 6/22/17 9:00 | 4 | 1610 | 4 | 1400 | -0.15
17 | Marketing - Launch of new product | Spain | Phase 4 - Manufacturing | 2017-01-10 09:00 | 33 | 882000 | 36 | 900000 | -0.01
17 | Marketing - Launch of new product | Spain | Phase 2 - Initiation | 10/16/17 9:00 | 42 | 196000 | 46 | 200000 | -0.01
17 | Marketing - Launch of new product | Spain | Phase 3 - Implementation | 2017-02-10 09:00 | 41 | 294000 | 45 | 300000 | -0.01
17 | Marketing - Launch of new product | Spain | Phase 1 - Planning | 8/21/17 9:00 | 56 | 98000 | 61 | 100000 | -0.01
58 | IT - CRM Implementation | Spain | Initiation | 2018-01-01 09:00 | 11 | 805 | 11 | 700 | -0.13
58 | IT - CRM Implementation | Spain | Preparation | 8/21/17 9:00 | 132.5 | 18515 | 105.5 | 16100 | -0.13
58 | IT - CRM Implementation | Spain | Development | 2017-01-09 09:00 | 96 | 24150 | 93 | 21000 | -0.13
58 | IT - CRM Implementation | Spain | Testing | 11/25/17 9:00 | 35.5 | 6440 | 33.5 | 5600 | -0.13
58 | IT - CRM Implementation | Spain | Deployment | 9/26/17 9:00 | 22 | 0 | 19 | 0 | -0.13
58 | IT - CRM Implementation | Spain | Post-deployment | 2017-12-09 09:00 | 9 | 3220 | 9 | 2800 | -0.13
51 | Marketing - Launch of new product | Sweden | Phase 1 - Planning | 2018-12-02 09:00 | 77.5 | 116000 | 61 | 100000 | -0.13
51 | Marketing - Launch of new product | Sweden | Phase 2 - Initiation | 2018-01-05 09:00 | 58.5 | 232000 | 46 | 200000 | -0.13
51 | Marketing - Launch of new product | Sweden | Phase 4 - Manufacturing | 2018-11-04 09:00 | 46 | 1044000 | 36 | 900000 | -0.13
51 | Marketing - Launch of new product | Sweden | Phase 3 - Implementation | 2018-12-04 09:00 | 57.5 | 348000 | 45 | 300000 | -0.13
79 | IT - CRM Implementation | Sweden | Initiation | 7/13/18 9:00 | 12.5 | 777 | 12.5 | 700 | -0.01
79 | IT - CRM Implementation | Sweden | Preparation | 2018-12-02 09:00 | 151 | 17871 | 129 | 16100 | -0.01
79 | IT - CRM Implementation | Sweden | Development | 2/25/18 9:00 | 109.5 | 23310 | 97.5 | 21000 | -0.01
79 | IT - CRM Implementation | Sweden | Testing | 2018-02-06 09:00 | 40.5 | 6216 | 2.5 | 5600 | -0.01
79 | IT - CRM Implementation | Sweden | Deployment | 3/25/18 9:00 | 25 | 0 | 19 | 0 | -0.01
79 | IT - CRM Implementation | Sweden | Post-deployment | 2018-09-03 09:00 | 10 | 3108 | 10 | 2800 | -0.01
23 | Marketing - Launch of new product | Switzerland | Phase 2 - Initiation | 4/28/18 9:00 | 56.5 | 244000 | 46 | 200000 | -0.06
23 | Marketing - Launch of new product | Switzerland | Phase 1 - Planning | 2018-12-02 09:00 | 74.5 | 122000 | 61 | 100000 | -0.06
23 | Marketing - Launch of new product | Switzerland | Phase 3 - Implementation | 2018-10-04 09:00 | 55 | 366000 | 45 | 300000 | -0.06
23 | Marketing - Launch of new product | Switzerland | Phase 4 - Manufacturing | 2018-08-04 09:00 | 44 | 1098000 | 36 | 900000 | -0.06
82 | IT - CRM Implementation | Switzerland | Initiation | 6/20/18 9:00 | 10.5 | 707 | 10.5 | 700 | -0.04
82 | IT - CRM Implementation | Switzerland | Preparation | 2018-12-02 09:00 | 127.5 | 16261 | 113.5 | 16100 | -0.04
82 | IT - CRM Implementation | Switzerland | Development | 2/23/18 9:00 | 92.5 | 21210 | 86.5 | 21000 | -0.04
82 | IT - CRM Implementation | Switzerland | Testing | 5/16/18 9:00 | 34.5 | 5656 | 30 | 5600 | -0.04
82 | IT - CRM Implementation | Switzerland | Deployment | 3/19/18 9:00 | 21 | 0 | 21 | 0 | -0.04
82 | IT - CRM Implementation | Switzerland | Post-deployment | 2018-05-03 09:00 | 8.5 | 2828 | 8.5 | 2800 | -0.04
25 | Marketing - Launch of new product | Togo | Phase 3 - Implementation | 2018-01-03 09:00 | 16 | 116000 | 15 | 100000 | -0.07
25 | Marketing - Launch of new product | Togo | Phase 4 - Manufacturing | 2/28/18 9:00 | 13 | 348000 | 12 | 300000 | -0.07
25 | Marketing - Launch of new product | Togo | Phase 1 - Planning | 2018-12-02 09:00 | 21.5 | 38666.6667 | 20.5 | 33333.3333 | -0.07
25 | Marketing - Launch of new product | Togo | Phase 2 - Initiation | 2018-06-03 09:00 | 16.5 | 77333.3333 | 15.5 | 66666.6667 | -0.07
89 | IT - CRM Implementation | Togo | Initiation | 3/20/18 9:00 | 3 | 256.6667 | 3 | 233.3333 | -0.12
89 | IT - CRM Implementation | Togo | Preparation | 2018-12-02 09:00 | 35.5 | 5903.3333 | 36.5 | 5366.6667 | -0.12
89 | IT - CRM Implementation | Togo | Development | 2/15/18 9:00 | 25.5 | 7700 | 28.5 | 7000 | -0.12
89 | IT - CRM Implementation | Togo | Testing | 2018-10-03 09:00 | 9.5 | 2053.3333 | 14.5 | 1866.6667 | -0.12
89 | IT - CRM Implementation | Togo | Deployment | 2/22/18 9:00 | 6 | 0 | 6 | 0 | -0.12
89 | IT - CRM Implementation | Togo | Post-deployment | 2/18/18 9:00 | 2.5 | 1026.6667 | 2.5 | 933.3333 | -0.12
32 | Marketing - Launch of new product | Turkey | Phase 1 - Planning | 2/17/18 9:00 | 33.5 | 63500 | 30.5 | 50000 | -0.05
32 | Marketing - Launch of new product | Turkey | Phase 2 - Initiation | 3/23/18 9:00 | 25.5 | 127000 | 23 | 100000 | -0.05
32 | Marketing - Launch of new product | Turkey | Phase 3 - Implementation | 3/15/18 9:00 | 25 | 190500 | 22.5 | 150000 | -0.05
32 | Marketing - Launch of new product | Turkey | Phase 4 - Manufacturing | 3/14/18 9:00 | 20 | 571500 | 18 | 450000 | -0.05
71 | IT - CRM Implementation | Turkey | Initiation | 2018-04-05 09:00 | 6.5 | 325.5 | 6.5 | 350 | -0.14
71 | IT - CRM Implementation | Turkey | Preparation | 2/17/18 9:00 | 75.5 | 7486.5 | 60 | 8050 | -0.14
71 | IT - CRM Implementation | Turkey | Development | 2/24/18 9:00 | 55 | 9765 | 44 | 10500 | -0.14
71 | IT - CRM Implementation | Turkey | Testing | 4/13/18 9:00 | 20.5 | 2604 | 7.5 | 2800 | -0.14
71 | IT - CRM Implementation | Turkey | Deployment | 2018-10-03 09:00 | 12.5 | 0 | 12.5 | 0 | -0.14
71 | IT - CRM Implementation | Turkey | Post-deployment | 2018-02-03 09:00 | 5 | 1302 | 5 | 1400 | -0.14
24 | Marketing - Launch of new product | Ukraine | Phase 2 - Initiation | 3/18/18 9:00 | 22 | 103000 | 23 | 100000 | -0.12
24 | Marketing - Launch of new product | Ukraine | Phase 1 - Planning | 2/17/18 9:00 | 29 | 51500 | 30.5 | 50000 | -0.12
24 | Marketing - Launch of new product | Ukraine | Phase 3 - Implementation | 2018-11-03 09:00 | 21.5 | 154500 | 22.5 | 150000 | -0.12
24 | Marketing - Launch of new product | Ukraine | Phase 4 - Manufacturing | 2018-11-03 09:00 | 17 | 463500 | 18 | 450000 | -0.12
74 | IT - CRM Implementation | Ukraine | Initiation | 2018-04-05 09:00 | 6.5 | 357 | 6.5 | 350 | 0
74 | IT - CRM Implementation | Ukraine | Preparation | 2/17/18 9:00 | 76 | 8211 | 45 | 8050 | 0
74 | IT - CRM Implementation | Ukraine | Development | 2/24/18 9:00 | 55.5 | 10710 | 49.5 | 10500 | 0
74 | IT - CRM Implementation | Ukraine | Testing | 4/14/18 9:00 | 20.5 | 2856 | 19 | 2800 | 0
74 | IT - CRM Implementation | Ukraine | Deployment | 2018-10-03 09:00 | 12.5 | 0 | 10.5 | 0 | 0
74 | IT - CRM Implementation | Ukraine | Post-deployment | 2018-02-03 09:00 | 5 | 1428 | 5 | 1400 | 0